## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
E01 | add new user | As a bank employee, I want to get a customer's name and credit value, and then verify the information. So that I can add new user into system. | 1 | 1 | 1.the users can join in the bank system through providing their real name in the credit agency. 2.the users can not join in the bank if they are not in the credit system. 3.the users can not rejoin in the bank if they are alreay in BankUser.csv (User name is unique). 4.make sure the successful-joined users information can be recorded in BankUser.csv |  | 3.22 | 4.05
E02a | create account | As a bank employee, I want to get a customer's name, account number, address, date of birth, and type of account. So that I can open a new account and generate a PIN for customer. | 1 | 1 | 1.both bank employees and logged-in users can create new accounts. 2.they need provide name, account number, address, date of birth, and type of account. 3.ensure the account number is unique. 4.ensure user who above the age of 16 can not open a Junior account. 5.ensure user who open a Current account have a overdraft limit while others don't have overdraft limit. 6.generate a PIN number ramdomly. 7.make sure users have a good credit status in Credit.csv otherwise they can not open an account. 8.make sure the successful-created accounts information can be recorded in Account.csv |  | 3.22 | 4.05
E02b | confirm credit status | As a bank employee, I want to check customer's credit value. So that I can allow the customer carry on to open account. | 1 | 1 | 1.open the users who have a more-than-50 credit value can open new accounts. |  | 3.22 | 4.05
E03a | login | As a customer, I want to enter my account through input account number and PIN. So that I can manage my account. | 2 | 2 | 1.users need provide their account number and PIN number to log in this system. 2.they can get notice if they enter the wrong information. |  | 4.06 | 4.2
E03b | logout | As a customer, I want to leave my account in a safe way. So that I can protect my account. | 2 | 2 | 1.users can leave this system and clear their account number and PIN number. 2.make sure users information are recoreded in Account.csv. |  | 4.06 | 4.2
E04 | customer menu | As a customer, I want to have a interface to select option. So that I can manage my account. | 2 | 2 | 1.users can get into this interface after login. 2.users can select which function they need. |  | 4.06 | 4.2
E05a | deposit funds | As a customer, I want to deposit some money after I login. So that I can deposit funds to this account. | 2 | 3 | 1.if the account was suspended, user can not use this function. 2.user can view this account's balance and overdraft value. 3.users can input the amount and type of funds they want to deposit. 4.only Current account users can select the pay off overdraft function, but if their balance are less than their overdraft, they can not pay off overdraft. 5.make sure the information is recorded into the Account.csv |  | 4.2 | 4.3
E05b | uncleared/cleared balance | As a customer, I want to choose the right type of money that I determine to deposit. So that I can deposit funds to this account as it should be. | 3 | 3 | 1.users can select which type of funds they want to save. 2.make sure the information is recorded into the "Balance" and "UnclearBalance" of Account.csv. |  | 4.2 | 4.3
E05c | pay off funds | As a customer, I want to pay off the funds that I overdrafted before in my current account. So that I can set my overdraft value into zero. | 5 | 4 | 1.only Current account users can select the pay off overdraft function. 2.but if their balance are less than their overdraft, they can not pay off overdraft. 3.make sure the information is recorded into the "Balance" and "Overdraft" of Account.csv. |  | 4.3 | 5.05
E06 | clear funds | As a bank employee, I want to clear the uncleared funds everyday 8 am. So that customer can get this funds in a fixed periord. | 2 | 5 | 1.uncleared Funds would be clear every day 8 am by the system. 2.make sure the current time can be get. 3.make sure the information is recoreded into the "Balance" and "UnclearBalance" of Account.csv. |  | 5.05 | 5.1
E07a | withdraw funds | As a customer, I want to withdraw some money after I login. So that I can withdraw funds from this account. | 2 | 3 | 1.if the account was suspended, user can not use this function. 2.user can view this account's balance, overdraft and overdraftlimit value. 3.users can input the amount of funds they want to withdraw. 4.only Current account users can select the overdraft function, but if their overdraftlimit-overdraft are less than their want to overdraft, they can overdraft successfully. 5.Saver account need to make a 2-day-before notice if they want to withdraw. 6.if the Saver account has already made a notice and now is in or after the reservation date, the Saver account user can withdraw; after withdraw successful, they should make a notice and wait for 2 days if they want to withdraw one more time. 7.make sure the information is recorded into the Account.csv |  | 4.2 | 4.3
E07b | overdraft funds | As a customer, I want to get extra money from my current account. So that I can use more money. | 3 | 4 | 1.only Current account users can select the overdraft function. 2.but if their overdraftlimit-overdraft are less than their want to overdraft, they can overdraft successfully. 3.make sure the information is recorded into the "Balance" and "Overdraft" of Account.csv. |  | 4.3 | 5.05
E07c | reservation for withdraw | As a customer, I want to make a notice before I do some withdrwal. So that I can withdraw funds from this account. | 2 | 5 | 1.if the account was suspended, user can not use this function. 2.only Saver accounts can use this function. 3.make sure the current time can be get. 4.if the Saver account has already made a notice and now is in or after the reservation date, the Saver account user can withdraw; after withdraw successful, they should make a notice and wait for 2 days if they want to withdraw one more time. |  | 5.05 | 5.1
E08a | suspend account | As a customer, I want to suspend my account, So that I can prevent any operation taking place. | 3 | 1 | 1.if an account was suspended, users can only unspended account, been clear funds, and close account. 2.make sure the information is recorded into Account.csv. |  | 3.22 | 4.05
E08b | unsuspend account | As a customer, I want to unsuspend my account, So that I can take operation in this account. | 3 | 1 | 1.users can not unsuspend when this account is not suspend. 2.users can have all the function after they unsuspend account. 3.make sure the information is recorded into Account.csv. |  | 3.22 | 4.05
E09 | close account | As a customer, I want to close my account, So that I will not have so many useless accounts. | 3 | 1 | 1.users can close account when the account was suspended. 2.but they can not close account when the cleared balance, unclear balance, or overdraft are not in zero. 3.make sure the user information will be delete in the Account.csv after close account successfully. |  | 3.22 | 4.05